## Deliverable Timeline
GASPS FY2011-2012 Requirements | DUE DATE
| OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP
PRE-ASSESSMENT
Hire/Identify a Program Coordinator | bar: DUE DATE NOV to DUE DATE JAN
Attend Georgia Strategic Prevention System (GASPS) orientation | bar: DUE DATE DEC
Attend required initial training (SPF Overview) | bar: DUE DATE DEC
Submit an organizational chart | bar: DUE DATE DEC
Submit an alcohol prevention Initiative staffing chart | bar: DUE DATE DEC
Join, establish and/or convene a Substance Abuse Prevention /Drug-free Community Coalition (aside from a Family Connection Collaborative) | bar: DUE DATE DEC to DUE DATE FEB
Convene the Community Prevention Alliance Workgroup (CPAW) consisting of 3 subworkgroups: 1) Epi workgroup 2) Planning & Operational Workgroup 3) Evaluation & Sustainability Workgroup | bar: DUE DATE DEC to DUE DATE FEB
Submit Partnership Agreements for the Community Prevention Alliance (MOUs, MOAs) | bar: DUE DATE DEC to DUE DATE FEB
Participate in the statewide Social Media Campaign | bar: DUE DATE DEC to DUE DATE SEP
ASSESSMENT
Attend required Needs Assessment (NA) Training | bar: DUE DATE JAN
Collect relevant data pertaining to the selected goals addressing each of the Interening Variables & Contributing Factors | bar: DUE DATE JAN to DUE DATE FEB
Attend required Capacity Building & Infrastructure (CB&I) Training | bar: DUE DATE FEB
Convene CPAW / key stakeholders meeting in the community. | bar: DUE DATE FEB to DUE DATE MAR
Submit CPAW meeting minutes with attached signature roster for CPAW-Epi wprkgroup/Planning & Operational workgroup/Evaluation & Sustainability workgroup with monthly report | bar: DUE DATE DEC to DUE DATE SEP
Assess community resources & readiness using provided tools & materials | bar: DUE DATE FEB to DUE DATE MAR
Submit a Cultural Competence report as part of capacity building draft report to RPS/SPAW to review for approval. | bar: DUE DATE MAR
Submit final Capacity Report to RPS/SPAW for review & approval. | bar: DUE DATE MAR
Identified and/or appropriate staff should become credentialed through the Prevention Credentialing Consortium of Georgia. At a minimum staff should be credentialed at the level of Prevention Apprentice within the first contract year. | bar: DUE DATE DEC to DUE DATE SEP
Submit a preliminary (draft) Needs Assessment Report to RPS/SPAW Review Panel. | bar: DUE DATE MAR
Submit a final Needs Assessment Report to RPS/SPAW for final approval | bar: DUE DATE MAR to DUE DATE APR
Evaluation Activities | bar: DUE DATE JAN to DUE DATE SEP
STRATEGIC PLANNING
Attend required Strategic Planning Training | bar: DUE DATE MAY
Develop and submit draft action plan that outlines selected evidence-based strategies and how these will be implemented using a logic model template and tools provided | bar: DUE DATE MAY to DUE DATE JUN
Submit a final action plan to RPS/SPAW for review and approval in order to move to implementation | bar: DUE DATE MAY to DUE DATE JUN
Attend required Evaluation Training | bar: DUE DATE MAY to DUE DATE JUL
Evaluation Activities | bar: DUE DATE JAN to DUE DATE SEP
Implementation & Sustainability
Attend required Implementation Training | bar: DUE DATE JUN to DUE DATE JUL
Attend required Sustainability Training | bar: DUE DATE JUN to DUE DATE AUG
Attend required MDS & Database Builder Training | bar: DUE DATE JAN to DUE DATE SEP
Submit a sustainability plan with letter of intent to RPS/SPAW for continuation approval | bar: DUE DATE AUG to DUE DATE SEP
Evaluation activities | bar: DUE DATE JAN to DUE DATE SEP
Attend required additional training related to the SPF model including workforce development, leadership & management skills, cultural competency, etc | bar: DUE DATE DEC to DUE DATE SEP
Submit Monthly Progress Report (MPR) |  |  |  | 2011-01-06 | 2011-02-07 | 2011-03-07 | 2011-04-06 | 2011-05-07 | 2011-06-07 | 2011-07-06 | 2011-08-07 | 2011-09-07